## WBS with Gantt Chart - BLANK
WORK BREAKDOWN STRUCTURE WITH GANTT CHART
PROJECT TITLE | PREDICTIVE MAINTENANCE FOR HVAC SYSTEMS IN A COMMERCIAL BUILDING
PROJECT MANAGER | MARRYLIND GRACE ANN ANAK JOHN
COMPANY NAME | BRAIN TECH
DATE | 2023-07-05 | [5 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Initiating
1.1 | Conduct Meeting with All Employees | 'Iffah | 2023-07-05 | 2023-07-05 | 1 | 0%
1.1.1 | State Objectives Of The Project | Arif | 2023-07-05 | 2023-07-07 | 2 | 0%
1.1.2 | Identify goals to be achieved at the end of the project | Izzah | 2023-07-05 | 2023-07-07 | 2 | 0%
1.1.3 | Identify skateholders that suit the project purposed | Marry | 2023-07-05 | 2023-07-07 | 2 | 0%
1.1.4 | Develop preliminary project scope for each learn | Izzah | 2023-07-05 | 2023-07-07 | 2 | 0%
2 | Planning
2.1 | Plan project cost | 'Iffah | 2023-07-11 | 2023-07-17 | 6 | 0%
2.1.1 | Acquire hardware and software that will used and tested | Arif | 2023-07-11 | 2023-07-17 | 6 | 0%
2.1.2 | Identify right amount of teammates needed | Marry | 2023-07-11 | 2023-07-17 | 6 | 0%
2.1.3 | Determine rate of wage of each employees involved | Marry | 2023-07-11 | 2023-07-17 | 6 | 0%
2.1.4 | Assume risk and determining cost needed to covered | 'Iffah | 2023-07-15 | 2023-07-28 | 13 | 0%
2.2 | Plan project milestone | Izzah | 2023-07-15 | 2023-07-28 | 13 | 0%
2.2.1 | Contribute task to each department and team | Arif | 2023-07-15 | 2023-07-28 | 13 | 0%
2.2.2 | Alert team regarding dateline for each milestone | Marry | 2023-07-15 | 2023-07-28 | 13 | 0%
2.3 | Plan the risk handling | 'Iffah | 2023-07-23 | 2023-08-03 | 10 | 0%
2.3.1 | List all possible risk before, during and after project development | Izzah | 2023-07-23 | 2023-08-03 | 10 | 0%
2.3.2 | Identify and record solution for each risk including people and resources | Arif | 2023-07-23 | 2023-08-03 | 10 | 0%
3 | Executing
3.1.1 | Perform Task based on milestone | Marry, Izzah, 'Iffah, Arif | 2023-08-03 | 2023-09-01 | 29 | 0%
3.1.2 | Collect resources required to be use in the task | Marry | 2023-08-03 | 2023-09-01 | 29 | 0%
3.1.3 | Collabortate with people that has been assigned on same task | Arif | 2023-08-03 | 2023-09-01 | 29 | 0%
3.1.4 | inform project manager once the task is completed or problem arise | 'Iffah | 2023-08-03 | 2023-09-01 | 29 | 0%
3.1.5 | Checklist for each workers in each task | Marry | 2023-08-03 | 2023-09-01 | 29 | 0%
3.2 | Execute alternative milestone | Izzah | 2023-08-03 | 2023-09-01 | 29 | 0%
3.2.1 | Execute new milestone if problem arise | 'Iffah | 2023-08-03 | 2023-09-01 | 29 | 0%
3.2.2 | Inform project manager if problems have been solve | Arif | 2023-08-03 | 2023-09-01 | 29 | 0%
4 | Control/Monitoring
4.1 | Evaluate completed task | Marry | 2023-08-28 | 2023-09-05 | 8 | 0%
4.1.1 | Run some sub-testiong on the product | Arif | 2023-08-28 | 2023-09-05 | 8 | 0%
4.1.2 | Record effectiveness and accuracy of product performance | Izzah | 2023-08-28 | 2023-09-05 | 8 | 0%
4.1.3 | Determine whether task has achieve the goal | Arif | 2023-09-10 | 2023-09-12 | 2 | 0%
4.2 | Iterate the project life cycle | 'Iffah | 2023-09-12 | 2023-09-18 | 6 | 0%
4.2.1 | Give result on satisfaction, if not satisfied redo planning and execution | 'Iffah, Izzah | 2023-09-14 | 2023-09-18 | 4 | 0%
5 | Closing
5.1 | Commercialize product | Arif | 2023-09-16 | 2023-09-19 | 3 | 0%
5.1.1 | Create document consists of detail of product | Marry, Izzah, 'Iffah, Arif | 2023-09-16 | 2023-09-19 | 3 | 0%
5.1.2 | Give product to the client | Izzah | 2023-09-16 | 2023-09-19 | 3 | 0%
5.1.3 | Collect feedback for improvement | Arif | 2023-09-16 | 2023-09-19 | 3 | 0%
5.2 | Clean-up the completed project | Arif | 2023-09-16 | 2023-09-19 | 3 | 0%
5.2.1 | Record entire project development | Izzah | 2023-09-16 | 2023-09-19 | 3 | 0%
5.2.2 | Conduct a post mortem meeting | Marry | 2023-09-16 | 2023-09-19 | 3 | 0%
5.2.3 | Record sources that may be reuse in fututre | 'Iffah | 2023-09-16 | 2023-09-19 | 3 | 0%